## Cover Page
Backbase_Practical Test_Test Cases
Created on: 24/May/2021
Generated by: Vinay Pandey
Powered by: Tricentis
Time zone: (GMT +05:30) India Standard Time
S No | Sheets | Descriptions | Links
1 | Test Case | This section of sheet, basic cases are written from the available specification document. I have created all the functional and UI test cases. | Test Case
2 | Defects | This section of sheet, covers all the bugs which were found during the manual testing | Defect
3 | Charts | This section of sheet, will show the graphical representation of the bus and test execution data | Charts

## Test Cases
DBID | Section Name | Id | Name | Status | Severity | Testing Type | Assigned To | Pre-Conditions | Test Data | Test Step # | Test Step Description | Test Step Expected Result | Actual Result | Images
208526384 | Alert Box | TC_01 | Verify and validate the BBlog URL. | Pass |  | Functional Testing | Vinay Pandey | 1- User should have valid URL 2- URL should be launched on browser first time. | https://qa-task.backbasecloud.com/. | 1 | Paste or type URL in the address bar of the browser. | User should get alert popup | Working as expected result
208538767 |  | TC_02 | Verify the cancel button functionality of JavaScript Popup alert. | Pass |  | Functional Testing | Vinay Pandey | 1- User should have valid URL 2- Website should be launched first time on the browser. 3- There should be a alert popup with Cancel and Sign In button. | https://qa-task.backbasecloud.com/. | 1 | Paste or type URL in the address bar of the browser. | User should get alert popup | Working as expected result
[6 empty] | Functional Testing |  |  |  | 2 | Click on "Cancel" button. | User should navigate to the page with the message "401 Authorization Required" | Working as expected result
|  | TC_03 | Verify the "Sing In" button functionality of javascript popup alert, when username and password is empty. | Pass |  | Functional Testing | Vinay Pandey | 1- User should have valid URL 2- Website should be launched first time on the browser. 3- There should be a alert popup with Cancel and Sign In button. | https://qa-task.backbasecloud.com/. | 1 | Paste or type URL in the address bar of the browser. | User should get alert popup | Working as expected result
|  | TC_04 |  | Pass |  | Functional Testing |  |  |  | 2 | Click on "Sign In" button. | Page should get reload and same popup alert should appear, with username, password, Cancel button and Sing In button. | Working as expected result
208538768 |  |  | Verify and validate the javascript popup with invalid username and empty password. | Pass |  | Functional Testing | Vinay Pandey | 1- User should have valid URL 2- Website should be launched first time on the browser. 3- There should be a alert popup with Cancel and Sign In button | https://qa-task.backbasecloud.com/. | 1 | Paste or type URL in the address bar of the browser. | User should get alert popup | Working as expected result
208538769 |  |  |  | Pass |  | Functional Testing |  |  | Username = test Password = | 2 | Enter the invalid username and keep the password field empty and click on the Sign In button. | Page should get reload and same popup alert should appear, with username, password, Cancel button and Sing In button. | Working as expected result
208538770 |  | TC_05 | Verify and validate the javascript popup with empty username and invalid password. | Pass |  | Functional Testing | Vinay Pandey | 1- User should have valid URL 2- Website should be launched first time on the browser. 3- There should be a alert popup with Cancel and Sign In button | https://qa-task.backbasecloud.com/. | 1 | Paste or type URL in the address bar of the browser. | User should get alert popup | Working as expected result
|  |  |  | Pass |  | Functional Testing |  |  | Username = Password = 123456 | 2 | Enter the invalid password and keep the username field empty and click on the Sign In button. | Page should get reload and same popup alert should appear, with username, password, Cancel button and Sing In button. | Working as expected result
208538771 |  | TC_06 | Verify and validate the javascript popup with valid username and password | Pass |  | Functional | Vinay Pandey | 1- User should have valid URL 2- Website should be launched first time on the browser. 3- There should be a alert popup with Cancel and Sign In button | Username: candidatex Password: qa-is-cool | 1 | Paste or type URL in the address bar of the browser. | User should get alert popup | Working as expected result
208538772 |  | TC_07 | Verify the popup alert when user refresh the page after entering the valid username and password. | Pass |  | Functional | Vinay Pandey | 1- User should be on the BBlog website. |  | 2 | Enter the valid username and password click on the Sign In button. | User should navigate to the BBlog website. | Working as expected result
|  |  |  | Pass |  | Functional |  |  | Username: candidatex Password: qa-is-cool | 1 | Refresh the webpage | User should navigate to the BBlog website. | Working as expected result
| Sign Up | TC_08 | Verify the header text of Sign Up | Fail |  | Functional | Vinay Pandey | User be on the sign up page. |  | 1 | Click on the sign up link of the header section of the page. | User should navigate to the Sign up page. | Working as expected result
[5 empty] | Low | Functional |  |  |  |  | Observer the header text of the sign up page. | There should be heading with "Sign up" text, above the "Have an account?" link | It is showing "Sign in" text. | Sign Up Heading text
|  | TC_09 | Functional | Pass |  | Functional | Vinay Pandey | Vinay Pandey | Username: test@test Email id: Password: | 1 | Enter the invalid Username as per test data and keep rest of the field empty and click on the "Sign up" button. | There should be proper error message for username, email id and password and user should not able to do sign up. | Working as expected result
|  | TC_10 | Verify and validate the sign up page functionality when all the fields are empty. | Fail | Low | Functional | Vinay Pandey | Vinay Pandey | Username: Email id: Password: |  | Keep the field empty and click on the "Sign up" button | There should be proper error message for username, email id and password and user should not able to do sign up. | There is no proper error message and message is not user friendly. | Error_Not_User_Friendly
|  | TC_11 | Verify and validate the sign up page functionality with invalid email id and rest of the data should be empty. | Pass |  | Functional | Vinay Pandey | 1- User should be on the "Sign up" page | Username: Email id: test Password: | 1 | Enter the invalid email id as per test data and keep rest of the field empty and click on the "Sign up" button. | There should be proper error message for username, email id and password and user should not able to do sign up. | Working as expected result
|  | TC_12 | Verify and validate the sign up page functionality with valid username and email id and password field should be empty. | Fail | High | Functional | Vinay Pandey | 1- User should be on the "Sign up" page | Username: Mobuserone Email id: mobuser@mob.com Password: | 1 | Enter the valid username and email id as per test data and keep password text field empty and click on the "Sign up" button. | There should be proper error message for password and user should not able to do sign up. | User is able to do sign up without entering password. | signupwithoutpassword
|  | TC_13 | Verify and validate the sign up page functionality with valid username and email id and password. | Pass |  | Functional | Vinay Pandey | 1- User should be on the "Sign up" page | Username: Mobusertwo Email id: mobusertwo@mob.com Password: 123456 | 1 | Enter the valid username, email id and password as per test data and click on the "Sign up" button. | User should able to complete the signup process successfully and he should be logged in. | Working as expected result
|  | TC_14 | Verify the response code in network tab | Fail |  | API | Vinay Pandey | 1- User should be on the "Sign up" page | Username: Mobusefive Email id: mobuserfive@mob.com Password: 123456 |  | Enter the valid username, email id and password as per test data and click on the "Sign up" button. Open the inspect element and go to the network tab. | Observe the response code it should be 201 | Response code is 200 | Response_Code
| Sign In | TC_15 | Verify and validate the sign in functionality with empty username and password. | Fail | Low | Functional | Vinay Pandey | 1- User should be on the "Sign in" page | Username: Password: | 1 | Click on the Sing in button and username and password should be empty. | User should get proper error message for Username and Password | User is getting error message for "Email can't be blank" | TextField_Is_Username_And_Error_Is_For_Email
|  | TC_16 | Verify and validate the sign in functionality with valid username and empty password. | Pass |  | Functional | Vinay Pandey | 1- User should be on the "Sign in" page | Username: vpandey@mobiquityinc.com Password: | 1 | Enter the valid username and keep password field empty and click on the Sing in button | Click on the Sing in button and username and password should be empty. | Working as expected result
|  | TC_17 | Verify and validate the sign in functionality with invalid username and password | Pass |  | Functional | Vinay Pandey | 1- User should be on the "Sign in" page | Username: #@@# Password: 2323 |  | Enter the username and password from the test data and click on the Sing in button. | User should not able to login and he should get a proper error message | Working as expected result | With_Space_Login
|  | TC_18 | Verify and validate the login functionality with space with prefix and suffix of email id. | Fail | Low | Functional | Vinay Pandey | 1- User should have valid email id and password. | Username: "info.vinaypandey@gmail.com " Password: 123456 | 1 | Launch the website. Navigate to the Sign in and enter the email id with space after the email id, and password and click on "Sign in" | User should get logged in. | User is not able to login.
|  | TC_19 | Verify and validate the sign in page functionality with valid username and password. | Pass |  | Functional | Vinay Pandey | 1- User should be on the "Sign up" page | Username: vpandey@mobiquityinc.com Password: 123456 |  | Enter the valid username and password as per test data and click on the "Sign in" button. | User should get logged in successfully. | Working as expected result
| Post (CURD) | TC_20 | Verify the "New Post" link navigation | Pass |  | Functional | Vinay Pandey | User should be logged in. | Username: vpandey@mobiquityinc.com Password: 123456 | 1 | Login in to the BBlog website using test data credential. | User should get logged in successfully. | Working as expected result
|  |  |  | Pass |  | Functional | Vinay Pandey |  |  | 2 | Click on the New Post text link, on the header section of the page. | User should navigate to the Publish Article page. | Working as expected result
|  | TC_21 | Verify and validate the "New Post" functionality with empty data for all fields. | Fail |  | Functional | Vinay Pandey | User should be logged in. | Username: vpandey@mobiquityinc.com Password: 123456 | 1 | Login in to the BBlog website using test data credential. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the New Post text link, on the header section of the page. | User should navigate to the Publish Article page and there should be following fields. 1- Article Title 2- What's this article about? 3- Write your article (in markdown) 4- Enter Tags 5- Publish Article button. | Working as expected result
[5 empty] | High | Functional |  |  |  | 3 | Click on the "Publish Article" button and keep all the fields empty | There should be a error message for the each and every respective fields and user should not able to create and publish the article | There is no error message, user can post empty article. | Empty Post
|  | TC_22 | Verify and validate the "New Post" functionality with valid data. | Pass |  | Functional | Vinay Pandey | User should be logged in. | Article Title: Lorem ipsum What's this article about?: Lorem ipsum Write your article : Enter the article data Enter Tags: Web | 1 | Login in to the BBlog website using test data credential. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the New Post text link, on the header section of the page. | User should navigate to the Publish Article page and there should be following fields. 1- Article Title 2- What's this article about? 3- Write your article (in markdown) 4- Enter Tags 5- Publish Article button. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Enter the valid data in the respective fields of the "New Post" and click in the Publish Article. | Article should get publish and it should display two buttons "Edit Article" and "Delete Article" button. | Working as expected result
|  | TC_23 | Verify the content of the articles publish by logged in user. (Read the article) | Pass |  | Functional | Vinay Pandey | User should be logged in. |  |  | Login in to the BBlog website using test data credential. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  |  | Click on the New Post text link, on the header section of the page. | User should navigate to the Publish Article page and there should be following fields. 1- Article Title 2- What's this article about? 3- Write your article (in markdown) 4- Enter Tags 5- Publish Article button. | Working as expected result
[6 empty] | Functional |  |  |  |  | Enter the valid data in the respective fields of the "New Post" and click in the Publish Article. | Article should get publish and it should display two buttons "Edit Article" and "Delete Article" button. | Working as expected result
[6 empty] | Functional |  |  |  |  | Click on the "Name of logged in user" on the header section page | User should navigate to the profile page and user should able to see "My Articles" tab. Here user should able to see the all the article publish by him | Working as expected result
[6 empty] | Functional |  |  |  |  | Click on any article "Read more.." text. | User should navigate to the same article detail page, where he/she can read the article. | Working as expected result
|  | TC_24 | Verify the "Delete Article" button functionality | Pass |  | Functional | Vinay Pandey | User should be logged in and he should have at least one article published. |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the title of the article | User should navigate to the page where he should able to see the two buttons "Edit Article" and "Delete Article" | Working as expected result
[6 empty] | Functional |  |  |  | 4 | Click on the "Delete Article" button. | Article should get deleted. | Working as expected result
|  | TC_25 | Verify the "Edit Article" button functionality | Pass |  | Functional | Vinay Pandey | User should be logged in and he should have at least one article published. |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the title of the article | User should navigate to the page where he should able to see the two buttons "Edit Article" and "Delete Article" | Working as expected result
[6 empty] | Functional |  |  |  | 4 | Click on the "Edit Article" button. | User should navigate to the edit article page and user should able to see the already added article data. | Working as expected result
[6 empty] | Functional |  |  |  | 5 | Do the changes in all the fields and click on "Publish Article" button. | Article should get publish with newly added data | Working as expected result
|  | TC_26 | Verify the UI of "Delete Article" button and "Edit Article" button on the article page. | Fail | Minor | Functional |  |  |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the "name" of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the "read more...". | User should navigate to the page where he should able to see the two buttons "Edit Article" and "Delete Article" | Working as expected result
[6 empty] | UI |  |  |  |  | Observe the "Edit Article" and "Delete Article" button UI | UI of the button should be proper | There is no space between two buttons | No_Spacing_Image
| Comment (CR*D) | TC_27 | Verify the comment functionality under the article page. | Pass |  | Functional | Vinay Pandey | User should be logged in and he should have at least one article published. |  | 1 | Login in to the BBlog website. | User should get logged in successfully.
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the "Read more..." text of the article | User should navigate to the page where he should able to see the "Write a comment..." textfield | Working as expected result
[6 empty] | Functional |  |  |  | 4 | Click on the comment box.. | Cursor should start blinking inside the comment box. | Working as expected result
[6 empty] | Functional |  |  |  | 5 | Enter the data in the comment section and click on "Post Comment" button | Comment should get post and user should able to see the comment and user should able to read the comment. | Working as expected result
|  | TC_28 | Verify the comment functionality under the article page with empty data. | Fail | Medium | Functional |  |  |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the title of the article | User should navigate to the page where he should able to see the "Write a comment..." textfield | Working as expected result
[6 empty] | Functional |  |  |  | 4 | Click on the text field. | Cursor should start blinking | Working as expected result
[6 empty] | Functional |  |  |  | 5 | Keep the comment section empty and click on "Post Comment" button. | User should get error message. | There is no error message, user is able to post the empty box comment | EmptyComment_Post
|  | TC_29 | Verify the delete comment functionality under the article page. | Pass |  | Functional | Vinay Pandey | User should be logged in and he should have at least one article published. |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the title of the article | User should navigate to the page where he should able to see the "Write a comment..." textfield | Working as expected result
[6 empty] | Functional |  |  |  | 4 | Click on the text field and observe the screen | cursor should start blinking | Working as expected result
[6 empty] | Functional |  |  |  | 5 | Enter the data in the comment section and click on "Post Comment" button | Comment should get post and user should able to see the delete icon image. | Working as expected result
[6 empty] | Functional |  |  |  | 6 | Click on the "delete icon" image | Comment should get delete. | Working as expected result
|  | TC_30 | Verify the default image the near comment button | Fail | Minor | Functional |  | 1- User should be logged in and he should have at least one article published. 2- There should be no profile image of the logged in user. |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the title of the article | User should navigate to the article detail page, where user can read the article. | Working as expected result
[6 empty] | UI Testing |  |  |  | 4 | Observer the image near the "Post Comment" | User should able to see the image default image near "Post Comment" button. | There is broken image, which should not be the case. | Click_Me_To_See_Broken_Image_Link
|  | TC_31 | Verify the UI of comment box | Fail |  | Functional |  | 1- User should be logged in and he should have at least one article published. |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the name of the user, which will displayed on the header section of the page. | User should navigate to the profile page where "My Articles" selected tab page. | Working as expected result
[6 empty] | Functional |  |  |  | 3 | Click on the title of the article | User should navigate to the article detail page, where user can read the article. | Working as expected result
[5 empty] | Trivial | Usability Testing |  |  |  | 4 | Observer the "Post Comment" box design | Design of the comment box should be proper. | Design of comment box is not proper, two boxes are visible | CommentBoxDesign
| Setting | TC_32 | Verify the UI when user upload big size of image on "Home, Profile, New Post and Setting page. | Fail | Trivial | Functional |  | User should have valid and big size image URL |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[6 empty] | Functional |  |  |  | 2 | Click on the "Setting" text link displayed on the header section of the page. | User should navigate to the "Setting" page. | Working as expected result
[5 empty] | Medium | UI Testing |  |  |  | 3 | User should navigate to the setting page and paste valid image URL in the "URL of profile picture" text field and click on the " Or click here to logout. " button and observe the "Home, Profile, New Post and Setting page. | Image should auto resize and UI should look good | UI is getting distorted | Distorted_Image
| Tags | TC_33 | Verify the Tags functionality when user create the article. | Pass |  |  |  |  | Article Title: Lorem ipsum What's this article about?: Lorem ipsum Write your article : Enter the article data Enter Tags: Web | 1 | Login in to the BBlog website using test data credential. | User should get logged in successfully. | Working as expected result
[10 empty] | 2 | Click on the New Post text link, on the header section of the page. | User should navigate to the Publish Article page and there should be following fields. 1- Article Title 2- What's this article about? 3- Write your article (in markdown) 4- Enter Tags 5- Publish Article button. | Working as expected result
[11 empty] | Click on the "Home" link text on the header of the page. | User should navigate to the "Home" screen | Working as expected result
[11 empty] | Enter all the data and tags, should be as per test data and click on the "Publish Article" button. | User should navigate to the newly created article screen. | Working as expected result
[11 empty] | Search the tag under the "Popular Tags" section and click on the new created tag | User should navigate to the list of all article which created under same tag.
|  | TC_34 | Verify the UI of tags, when user enter long data. | Fail | Medium | UI |  | User should be logged in. | Tags: AutoTest Article Create Tag 1AutoTest Article | 1 | Login in to the BBlog website using test data credential. | User should get logged in successfully. | Working as expected result
[10 empty] | 2 | Click on the New Post text link, on the header section of the page. | User should navigate to the Publish Article page and there should be following fields. 1- Article Title 2- What's this article about? 3- Write your article (in markdown) 4- Enter Tags 5- Publish Article button. | Working as expected result
[10 empty] | 3 | Enter all the data and tags, should be as per test data and click on the "Publish Article" button. | User should navigate to the newly created article screen. | Working as expected result
[10 empty] | 4 | Search the tag "AutoTest Article Create Tag 1AutoTest Article " under the "Popular Tags" section and observe the UI of the tag. | UI of text should be proper. | UI of tag text is not proper. Note: Until character limit 29, design is not getting distorted | Tag_Inside_Article
| URL Manipulation | TC_35 | Verify that user can manipulate the URL and access the data of ther others articles. | Fail | Medium | Functional |  | User should be logged in. |  | 1 | Login in to the BBlog website. | User should get logged in successfully. | Working as expected result
[10 empty] | 2 | Click on the "Global Feed" tab on the home screen. | User should able to see all the articles. | Working as expected result
[10 empty] | 3 | Click on "Read more..." text of any other user article. | User should navigate to the "Article page"
[10 empty] | 4 | On the same page, do the changes in the URL "article" to "editor" for example https://qa-task.backbasecloud.com/#/article/climate-title-qbbf40 to https://qa-task.backbasecloud.com/#/editor/climate-title-qbbf40 And Press Enter button | User should navigate to the "Home" screen | User is able to see the edit screen of the user user article. | URL_Manipulation

## Defect
BUG ID | Issue Type | Priority | Severity | Bug Title | Test Steps | Expected Result | Actual Result | Visual Evidence
BI_001 | Functional | Low | Low | Heading of the "Sign up" is wrong | Click on the "sign up" text link on the header of the page. | There should be heading with "Sign up" text, above the "Have an account?" link | It is showing "Sign in" text. | Sign Up Heading text
BI_002 | Functional | Low | Low | Verify and validate the sign up page functionality when all the fields are empty. | 1- Launch Application 2- Navigate to the sign up screen. 3- Keep all the fields empty and click on the sign up button. | There should be proper error message for username, email id and password and user should not able to do sign up. | There is no proper error message and message is not user friendly. | Error_Not_User_Friendly
BI_003 | Functional | High | High | User is able to do sign up without password. | 1- Launch Application 2- Navigate to the sign up screen. 3- Enter the valid user name and password and keep the password text field empty and click on the "Signup" button. | There should be a error message and user should not able to login. | User is able to login into the application. | signupwithoutpassword
BI_004 | Functional | Low | Low | User is not able to login if email, there space prefix or suffix of email id. | "1- Launch Application 2- Enter the email id " info.vinaypandey@gmail.com " and password "123456" | User should able to login into the application. | User is not able to login in the application. | With_Space_Login
BI_005 | Functional | Low | Low | Wrong error message for the empty username text field. | 1- Launch Application 2- Navigate to the sign up screen. 3- Keep username and password text field and click on the "Sign up" button. | User should get error message for username | User is getting error message for email id. | TextField_Is_Username_And_Error_Is_For_Email
BI_006 | Functional | High | Low | Empty article can be posted, no validation. | 1- Launch Application 2- Login into the application 3- Click on the "New Post" 4- Keep all the fields empty and click on the "Publish Article button" | There should be a error message for the each and every respective fields and user should not able to create and publish the article | There is no error message, user can post empty article. | Empty Post
BI_007 | UI | Low | Low | Button alignment issue | 1- Launch Application 2- Login into the application 3- Create a post and navigate to the article create by logged in user. 4- Observe the "Edit Button" and "Delete Button" alignment. | Alignment of the buttons should be proper and there should be a proper spacing | There is no spacing between the two buttons. | No_Spacing_Image
BI_008 | Functional | Medium | Medium | Empty comment can be posted, no validation. | 1- Launch Application 2- Login into the application 3- Navigate to the article. 4- Keep the comment box empty and click on the "Post Comment" button | User should get proper error message | User can post the comment and there is no error message. | EmptyComment_Post
BI_009 | Functional | Low | Low | User is getting broken image near "Post Comment" button when logged in user has not uploaded his image. | 1- Launch Application 2- Login into the application 3- Navigate to the article, created by him. 4- Observe the image near "Post Comment" button. | User should able to see the default image near post button. | Broken image is shown in the chrome browser and in safari it is showing "?" question mark. | Click_Me_To_See_Broken_Image_Link
BI_010 | Functional | Low | Low | UI of the comment box is not proper. | 1- Launch Application 2- Login into the application 3- Navigate to the article, created by him. 4- Observe the UI of the comment box. | UI of the comment box should be proper. | Design of comment box is not proper, two boxes are visible
BI_011 | Functional | Medium | Low | There is no image resizing functionality, due to which design of the website is getting distorted. | 1- Login in to the BBlog website. 2- Click on the "Setting" text link displayed on the header section of the page. 3- User will navigate to the setting page and paste valid image URL in the "URL of profile picture" text field and click on the " Or click here to logout. " button and observe the "Home, Profile, New Post and Setting page. | After uploading image, website should not get distorted | UI is getting distorted | Distorted_Image
BI_012 | UI | Low | Low | UI of the tags | Navigates to the "Home" page, verify the UI of tags under the "popular tags" | Long text tags are not aligned | UI is getting distorted | Tag_Inside_Article
BI_013 | Functional | High | High | URL manipulation | 1- Login in to the BBlog website. 2- Click on the "Global Feed" tab on the home screen. 3- Click on "Read more..." text of any other user article. "On the same page, do the changes in the URL ""article"" to ""editor"" for example https://qa-task.backbasecloud.com/#/article/climate-title-qbbf40 to https://qa-task.backbasecloud.com/#/editor/climate-title-qbbf40" 4- And Press Enter button | User should navigate to the "Home" screen | User is able to see the edit screen of the user user article. | URL_Manipulation
BI_014 | API | Low | Low | Response code, after sign up | 1- Launch Application 2- Navigate to the sign up page 3- Create the account, with valid data, open the network from inspect elements and observe the response code. | Response code should be 201 | Response code is 200. | Response_Code
BI_015 | API | Low | Low | API call with false URL | "1- Launch Application 2- Login into the application 3- Navigate to the article. 4- Enter the details in the article page and click on the "Publish Article" button 5- Observe the numm point URL is called. Note: Open Network tool | False URL should not be triggered | Null point URL is getting call | Null_Point_URL

## Charts
Test Results | Percentage | Summary | Percentage
Pass | 57.1429 | Total Test Case Created | 35
Fail | 42.8571 | Total Test Case Executed | 35
|  | Total Test Case Pass | 20
|  | Total Test Case Fail | 15